## WeeklyRosterReport
M/C | Day | Start Time | Finish Time | Location | Sts | REM | Path | From | To | Crew Manager | Operators | conductor | DRA
73946 | Sat | 01:00 | 08:30 | RYLSTONE BRANCH | Live | PL |  | Skipton | Skipton
75402 | Sat/Sun | 23:30 | 07:30 | Longbeck | Live | PL3 |  | Middlesbrough | Middlesbrough
75402 | Sat/Sun | 23:30 | 07:30 | Longbeck | Live | PL3 |  | Middlesbrough | Middlesbrough
75505 | Sat/Sun | 23:45 | 08:15 | CONNINGTON SOUTH | Live | S&C |  | Huntingdon | Peterborough Eastfield
75506 | Sat/Sun | 23:45 | 08:15 | CONNINGTON SOUTH | Live | S&C |  | Huntingdon | Huntingdon
77802 | Sun | 01:05 | 08:00 | Navarino Rd Jn to Lea Jn | Live | Reg |  | Broxbourne | Broxbourne
77802 | Sun/Mon | 22:30 | 04:35 | Cannonbury to Hackney Central | Live | Reg |  | Broxbourne | Broxbourne
75506 | Sun/Mon | 23:55 | 04:45 | Werrington & Tallington | Live | PL |  | Huntingdon | Peterborough Eastfield
75503 | Sun | 00:15 | 08:00 | DONCASTER STATION DOWN | Live | S&C |  | Doncaster Marshgate | Doncaster Marshgate
75404 | Sun | 00:20 | 07:50 | Langley Mill to Alfreton | Live | S&C |  | Trent Siding | Trent Siding
75405 | Sun | 00:20 | 07:50 | Langley Mill to Alfreton | Live | S&C |  | Trent Siding | Trent Siding | Balal Testing,
77801 | Sun | 00:25 | 08:05 | Dore Station - Charlotte Road | Live | Reg |  | Doncaster Marshgate | Doncaster Marshgate
75302 | Sun | 00:30 | 06:00 | Knebworth to Stevenage | Live | S&C |  | Welwyn Garden City | Welwyn Garden City
75303 | Sun | 00:30 | 06:00 | Knebworth to Stevenage | Live | S&C |  | Welwyn Garden City | Welwyn Garden City
77802 | Mon/Tue | 22:45 | 04:40 | Ely North to Kings Lynn | Live | Reg |  | Downham Market | Downham Market
77801 | Mon/Tue | 23:05 | 05:50 | St Neots | Live | Reg |  | Huntingdon | Huntingdon
75405 | Mon/Tue | 23:55 | 04:50 | Derby London Road Jn to St. Marys South Jn | Live | PL |  | Trent Siding | Trent Siding
75404 | Mon/Tue | 23:55 | 05:00 | Sheet Stores Jn to Stenson Jn | Live | PL |  | Trent Siding | Trent Siding
75402 | Tue | 01:00 | 05:25 | DAWDON - RYHOPE | Live | PL3 |  | Middlesbrough | Middlesbrough
77802 | Tue/Wed | 22:45 | 04:40 | Littleport to Downham Market | Live | Reg |  | Downham Market | Downham Market
77801 | Tue/Wed | 23:05 | 05:50 | Sandy | Live | Reg |  | Huntingdon | Huntingdon
75405 | Tue/Wed | 23:45 | 05:40 | Ambergate Jn to Clay Cross Tunnel | Live | PL |  | Trent Siding | Trent Siding
75404 | Tue/Wed | 23:55 | 05:00 | Sheet Stores Jn to Stenson Jn | Live | PL |  | Trent Siding | Trent Siding
73946 | Tue | 00:01 | 05:30 | Bridlington 200 A/B pts | Live | S&C |  | Driffield | Driffield
75505 | Tue | 00:05 | 05:25 | Hitchin South | Live | PL |  | Huntingdon | Welwyn Garden City | Abid Hussain, | Balal Testing,
75402 | Wed | 01:00 | 05:25 | DAWDON - RYHOPE | Live | PL3 |  | Middlesbrough | Middlesbrough
77802 | Wed/Thu | 22:45 | 04:40 | Downham Market to Watlington | Live | Reg |  | Downham Market | Downham Market
77801 | Wed/Thu | 23:05 | 05:50 | Cardells to Huntingdon South | Live | Reg |  | Huntingdon | Huntingdon
75402 | Wed/Thu | 23:40 | 04:50 | Glaisdale | Live | PL3 |  | Middlesbrough | Middlesbrough
75405 | Wed/Thu | 23:55 | 05:20 | Willington to Wetmore Jn | Live | PL |  | Trent Siding | Trent Siding
75505 | Wed | 00:05 | 05:25 | Stevenage North | Live | PL |  | Welwyn Garden City | Welwyn Garden City | Abid Hussain,
77802 | Thu/Fri | 22:45 | 04:40 | Downham Market to Watlington | Live | Reg |  | Downham Market | Downham Market
77801 | Thu/Fri | 23:05 | 05:50 | Little Barford | Live | Reg |  | Huntingdon | Huntingdon
75402 | Thu/Fri | 23:40 | 04:50 | Glaisdale | Live | PL3 |  | Middlesbrough | Middlesbrough
75405 | Thu/Fri | 23:55 | 05:20 | Willington to Wetmore Jn | Live | PL |  | Trent Siding | Trent Siding
75505 | Thu | 00:05 | 05:25 | Langley Junction | Live | PL |  | Welwyn Garden City | Welwyn Garden City | Abid Hussain,Balal Testing,